## Matrix
Fall 2018 Bulletin Process Map Matrix
Instruction & Student Services | [6 empty] | 2018-03-27 |  | 2018-04-12 | [6 empty] | 2018-06-27 |  | 2018-06-29
[7 empty] | AA posts PDF to web-1st link=Front Cover, 2nd link=schedule |  | Copies of Bulletin ready for distribution | REPRINT | [5 empty] | AA posts PDF to web 1st link is Front Cover 2nd link is schedule |  | Copies of Bulletin ready for distribution
[7 empty] | 10 | [8 empty] | 11
Registrar |  | 2018-03-02 |  |  | 2018-03-20 | [5 empty] | 2018-06-06 |  |  | 2018-06-20
|  | Completes scheduling |  |  | Done making edits. Submit to IR by 5pm | [5 empty] | Done making edits. Submit to IR by 5pm |  |  | Done making edits. Submit to IR by 5pm
|  | 3 |  |  | 6 | [5 empty] | 2 |  |  | 7
Institutional Research | 2018-02-22 |  | 2018-03-07 |  | 2018-03-20 | 2018-03-27 |  |  |  |  | 2018-06-06 | 2018-06-12 |  | 2018-06-20 | 2018-06-26
| Submits semester dates to Ray |  | Proof is distributed to Bulletin Group 8am |  | Done making edits 5pm | Saves final PDF in T:\Bulletin 5pm |  |  |  |  | Done making edits by 5pm | Proof is distributed to Bulletin Group 8am |  | Done making edits by 5pm | Saves final PDF in T:\Bulletin 5pm
| 1 |  | 4 |  | 7 | 9 |  |  |  |  | 3 | 5 |  | 8 | 10
Print Shop |  |  |  |  | 2018-03-20 |  |  | 2018-03-29 |  |  | 2018-06-06 |  |  | 2018-06-20 |  |  | 2018-06-27
[5 empty] | Done making edits by 5pm |  |  | Gets final draft from T:\Bulletin, prints 1000 copies 8am |  |  | Done making edits |  |  | Done making edits by 5pm |  |  | Gets final draft from T:\Bulletin, prints 1000 copies at 8am
[5 empty] | 8 |  |  | 11 |  |  | 4 |  |  | 9 |  |  | 12
Bulletin Group | 2018-02-22 |  |  | 2018-03-12 | [5 empty] | 2018-05-30 |  |  | 2018-06-18
| Course scheduling changes due by 5pm |  |  | Submit updates to: Registrar=schedule, IR=Front, Print Shop=WTCE by 5pm | [5 empty] | Submit updates to: Registrar=schedule, IR=Front, Print Shop=WTCE by 5pm |  |  | Submit updates to: Registrar=schedule, IR=Front, Print Shop=WTCE by 5pm
| 2 |  |  | 5 |  |  |  |  | 12 | 1 |  |  | 6 |  |  |  |  | 13